## Sprint 1 Retrospective
Navi-Gator — Sprint 1 Retrospective Commitments
Team members: Vyrareth (PO), Don, Edgar, Cristofer, Nitin ¦ Sprint 1 ¦ Submitted 10/13/2026
1. Planned Tasks COMPLETED in Sprint 1
# | Task | Owner | Category | Status | Verification / Proof
1 | SQL image database schema (County → Sector → Road → Segment) | Don | Backend / DB | Completed | Setup script runs; all 5 tables + columns created (tested by PO).
2 | Front end ↔ Flask ↔ SQLite integration | Nitin | Full-stack | Completed | PO ran app: page served, map + dropdowns driven from DB; /locations JSON OK (PR #1).
3 | Cloudflare R2 image storage set up (buckets live) | Edgar | Infrastructure | Completed | R2 API confirms 2 live buckets (street-images, sectors).
4 | Hosting & storage decision (R2 + GitHub LFS; AWS dropped) | Team | Decision | Completed | Documented in Design doc; AWS evaluated and dropped on cost.
5 | NJGIN sector grid mapped & named (A–W × 1–29) | Don | Data / Research | Completed | Sector names + bounding boxes feed the sector table.
6 | Auto-screenshot prototype (coordinate → satellite snapshot → file) | Cristofer | Backend / Prototype | Completed | Zooms to a coordinate, captures snapshot, saves to file; coordinate is the input.
7 | Image preprocessing — road mask (contrast / B&W) | Don | Backend / Prototype | Completed | scikit-image: invert → CLAHE → threshold produces a B&W road mask.
8 | Requirements document (template filled) | Vy | Documentation | Completed | Completed to course template.
9 | Design document (architecture, data model, hosting) | Vy | Documentation | Completed | Reflects current build (schema, R2, Flask, preprocessing).
10 | Sprint 1 Product Backlog + Trello board updated | Vy | PO / Docs | Completed | Board renamed to Sprint 1; cards updated.
2. Planned Tasks NOT Completed in Time (reason for delay + action plan)
# | Task | Owner | Reason for Delay | Action Plan | Target Sprint
1 | Road isolation + centerline / coordinate extraction | Don | The initial scikit-image approach (contrast + morphology + pixel trace) hit accuracy walls — shadow and tree noise and unreliable road continuity. Preprocessing works, but reliable road isolation did not. | Move to backlog. Pivot to a published road-extraction method (Li & Briggs, 2009) the dev researched; re-implement isolation on that basis. Rough-coordinate algorithm stays, with added specification. | Sprint 2
2 | Populate image database with sector / road screenshots | Cristofer / Don | Auto-screenshot is complete, but targeted capture + DB population depend on road coordinates (task above), so it could not start. | Once road coordinates land, batch-capture sectors via the auto-screenshot tool and load file locations into the DB. | Sprint 2
3 | CNN road-condition classification (pothole / road quality) | Don / Team | Blocked upstream: needs labeled road-segment images in the DB, which depend on the two tasks above. | Keep in backlog; begin once segment screenshots are flowing. Start collecting / labeling sample images in parallel so the model is ready. | Sprint 2–3
4 | Condition-aware routing (shortest 'good' route) | Nitin / Edgar | Base map + DB-driven locations are live, but weighting roads by condition needs the CNN output, which isn't ready yet. | Keep the baseline Geoapify / Leaflet route; add road-condition edge weighting once classification output exists. | Sprint 2–3
Team note on the delays:
Sprint 1 ran through the exam period, so overall velocity was lower than planned and some product-owner upkeep (backlog grooming, mid-sprint check-ins) lagged. The biggest technical miss was road isolation: the first image-processing approach did not produce reliable road geometry, so the dev researched and is adopting an alternate published method — the trade-off is that extracted roads won't be pixel-exact to the source image, which is acceptable for our routing use. Most remaining misses are a dependency chain off that one task, not separate failures. Commitment for Sprint 2: a fixed weekly backlog-grooming + check-in cadence, keep Trello current per task, and unblock the road-isolation task first so the capture → DB → classification → routing chain can move.