## Sprint 1 Review
Navi-Gator — Sprint 1 Review & Carryover
Team: Vyrareth (PO), Don, Edgar, Cristofer, Nitin ¦ Sprint 1 → Sprint 2 ¦ 10/16/2026
1. Planned Tasks COMPLETED in Sprint 1
# | Task | Owner | Status
1 | SQL image database schema (County → Sector → Road → Segment) | Don | Completed (tested)
2 | Front end ↔ Flask ↔ SQLite integration | Nitin | Completed (PO-tested, PR #1)
3 | Cloudflare R2 image storage set up (buckets live) | Edgar | Completed (API-verified)
4 | Hosting & storage decision (R2 + GitHub LFS; AWS dropped) | Team | Completed
5 | NJGIN sector grid mapped & named (A–W × 1–29) | Don | Completed
6 | Auto-screenshot prototype (coordinate → snapshot → file) | Cristofer | Completed
7 | Image preprocessing — road mask (contrast / B&W) | Don | Completed
8 | Requirements & Design documents | Vy | Completed
9 | Definition of Done (Sprint 0 & 1) + Acceptance / Validation docs | Vy | Completed
10 | Product Backlog + Trello board + Sprint 1 Retrospective | Vy | Completed
2. Planned Tasks NOT Completed — Carryover to Sprint 2
Card | Task | Owner | Reason for Delay | Action Plan | Anticipated Completion
S1-8-B | Road Mapping Coordinate-finding System | Don (DF) | The initial scikit-image approach (contrast + morphology + pixel trace) could not reliably isolate road geometry — shadow/tree noise and broken road continuity. Testing also showed NJGIN overhead resolution limits fine detail. | Move to Sprint 2. Pivot to a published road-extraction method (Li & Briggs, 2009); re-implement isolation and output road/segment coordinates. Rough-coordinate algorithm is retained. | Sprint 2 — Wk 2 (target 10/29/2026)
S1-8 | Database Population B; Road/Segment-level Population & Auto-Screenshot | Vy, Cristofer, Don (VK/CS/DF) | Blocked on S1-8-B: the auto-screenshot tool is complete, but road/segment-level capture needs the coordinates from the coordinate-finding system to know where to capture. Could not start population without them. | Move to Sprint 2 (after S1-8-B). Batch-run auto-screenshot across sector/road/segment coordinates, then load image file locations into the DB and verify. | Sprint 2 — end (target 11/05/2026)

## Sprint 2 Get-Well Plan
Sprint 2 — Get-Well Plan for Carryover Tasks
How the two carryover tasks will be completed, by whom, and when. Target dates are proposed and to be confirmed at Sprint 2 planning.
Dependency: S1-8-B (coordinates) must finish before S1-8 (population) can run. They are sequenced, not parallel.
S1-8-B · Road Mapping Coordinate-finding System
Owner: Don
Step | What we do | Owner | Done when… | Target date
1 | Implement the Li & Briggs (2009) road-extraction method on sample NJGIN sectors (replace the scikit-image isolation step). | Don | Method runs on a sector tile and outputs a clean road mask. | 10/22/2026
2 | Validate centerline / coordinate output on 3–5 known roads; tune thresholds. | Don | Extracted road lines match the real roads on known samples. | 10/26/2026
3 | Write road & segment coordinates into the schema (road / segment tables). | Don | Road/segment records populate with lat/long + bounds. | 10/29/2026
S1-8 · Database Population B; Road/Segment Population & Auto-Screenshot
Owner: Vy, Cristofer, Don
Step | What we do | Owner | Done when… | Target date
1 | Once coordinates land (S1-8-B), batch-run the auto-screenshot tool across sector / road / segment coordinates. | Cristofer | Snapshots captured and saved for each target coordinate. | 11/01/2026
2 | Load captured image file locations into the DB (sector / road / segment tables). | Don / Vy | DB rows reference the correct image files per segment. | 11/03/2026
3 | Verify populated records and spot-check a sample of images. | Vy | Counts match expected; sampled images are the right roads. | 11/05/2026
Anticipated full completion of both carryover tasks: end of Sprint 2 — target 11/05/2026.